## Working Project Plan
Task | Start Date | Due Date | Status | Done | Notes such as what changes were made
Initial Plan | 2021-04-19 | 2021-04-19 | DONE | TRUE | Started Late
Plan out solution | 2021-04-29 | 2021-04-19 | STARTED | FALSE | Started Late
Design notebook | 2021-04-29 | 2021-04-22 | STARTED | FALSE | Started Late
Create the Poll | 2021-04-25 | 2021-04-21 | STARTED | FALSE | Started Late
Data Collection | 2021-04-25 | 2021-04-29 | STARTED | FALSE | Started Late
Create the Skeleton functions | 2021-04-30 | 2021-04-24 | STARTED | FALSE | Started Late
Code all the functions | 2021-05-01 | 2021-04-28 | STARTED | FALSE | Started Late
Code main | 2021-05-01 | 2021-04-29 | STARTED | FALSE | Started Late
Test Program | 2021-05-01 | 2021-04-30 | STARTED | FALSE | Started Late
Polish Code | 2021-05-01 | 2021-04-30 | STARTED | FALSE | Started Late
Polish Design Notebook | 2021-05-01 | 2021-04-30 | STARTED | FALSE | Started Late
Turn everything in | 2021-05-01 | 2021-04-30 | STARTED | FALSE | Started Late

## Original Project Plan
Task | Start Date | Due Date | Status | Done | Notes such as what changes were made
Initial Plan | 2021-04-17 | 2021-04-19 | DONE | FALSE
Plan out solution | 2021-04-19 | 2021-04-19 | NOT STARTED | FALSE
Design notebook | 2021-04-21 | 2021-04-22 | NOT STARTED | FALSE
Create the Poll | 2021-04-21 | 2021-04-21 | NOT STARTED | FALSE
Data Collection | 2021-04-21 | 2021-04-29 | NOT STARTED | FALSE
Create the Skeleton functions | 2021-04-24 | 2021-04-24 | NOT STARTED | FALSE
Code all the functions | 2021-04-26 | 2021-04-28 | NOT STARTED | FALSE
Code main | 2021-04-28 | 2021-04-29 | NOT STARTED | FALSE
Test Program | 2021-04-29 | 2021-04-30 | NOT STARTED | FALSE
Polish Code | 2021-04-30 | 2021-04-30 | NOT STARTED | FALSE
Polish Design Notebook | 2021-04-30 | 2021-04-30 | NOT STARTED | FALSE
Turn everything in | 2021-04-30 | 2021-04-30 | NOT STARTED | FALSE